Terms of Reference ref.no. RFP-POL-00011

RESEARCH CONSULTANCY ON OPPORTUNITIES TO ENHANCE INCLUSIVITY OF PUBLIC PARTICIPATION MECHNISMS TOWARDS DISPLACEMENT-AFFECTED PERSONS IN POLAND AND RELATED DISSEMINATION AND OPERATIONALIZATION WORKSHOPS

GENERAL BACKGROUND

The Danish Refugee Council (DRC) is a leading protection agency with a mandate to promote and protect durable solutions to conflict and displacement affected populations on the basis of humanitarian principles and human rights. DRC is implementing a multi-sector response to support Ukraine refugees, IDPs and host populations both within Ukraine and in the neighboring countries of Poland, Romania and Moldova and wider Europe.

Since late February 2022, nearly 4 million Ukrainians and third-country nationals have crossed the border to Poland. As part of its neighboring country response, DRC established an operational presence in Poland to support displaced populations through partnership with civil society organizations and national NGOs, duty bearers and other actors.  DRC supports partners in providing protection services to conflict-affected persons in particular legal aid/legal counselling, psychosocial support, access to information, referrals. DRC also supports several collective sites through Site Management Support (SMS). Globally, DRC together with UNHCR is co-leading the Protection Information Management Initiative (PIM initiative). The above factors, in addition to DRC’s global expertise in protection information management incl. protection monitoring, provide opportunities for synergies between ongoing protection response implemented primarily through partnerships and protection monitoring, placing DRC in a position of unique advantage to lead the process in collaboration with its broad network of partners and in coordination with the Protection Sector in Poland.

According to the UNHCR data, from 24 February till the first half of February 2023 (almost a year after the Ukraine War crisis), 750.809 refugees have crossed from Ukraine to Moldova. While majority continued their journey toward EU, compared specifically to the domicile population, still a significant number of refugees remain in the country 108,885 refugees. Danish Refugee Council has engaged in the response in the Republic of Moldova in March 2022 and since then has been delivering assistance through implementing partners and directly, mainly in the sectors of Protection, EORE, Site Management and Support, Livelihood Enhancement and Community-based response.

Context of the Assignment

In collaboration with 12 Poland–based NGOs, DRC is providing comprehensive protection services to displacement-seekers, migrants and host community - in 7 locations in Poland. The project puts a special focus on community engagement and participation, including through community-driven initiatives. The meaningful participation of representatives of displaced communities in policy and decision making processes together with the host community, enhances social cohesion, creates opportunities to recognise protection risks and needs faced by the affected population as well as their resources, capacities and preferences,  fosters the inclusion of their experience and expertise in the elaboration of local policies, and promotes stronger and more inclusive democratic institutions  and policies at local level, which are more encompassing of the needs and preferences of all inhabitants. On the other hand, the proactive role and vast experience of the Polish civil society in advocacy and collaboration with local authorities open the window of opportunity to create a nexus between Ukrainian and Polish activists and local policymakers. To this end, DRC Polska is looking for an experienced external consultant with capacity to conduct research to map the available participatory mechanisms in the areas where DRC Polska implements activities(directly or through partners), map the existing social structures of the displaced population and prepare recommendations for NGOs and municipalities on the ways to strengthen the inclusion of displacement-affected persons in public participation mechanisms at municipal level.

The expected start of the contract is from September 25th 2023 for a period of 75 days.

Study objectives:

A key objective of the assignment is to provide:

Mapping of existing public participation mechanisms, budgets, micro-grants, etc. for children, youth, adults and elderly in the municipalities and public institutions (I.e. Schools) in Gdynia, Warsaw, Lublin, Wroclaw, Rzeszow, Przemysl and Krakow, inter alia participatory budgets.

Conduct research on the barriers and opportunities in the access to those mechanisms through desk research (policy and policy documents analysis) secondary data review, and through key informant interviews, focus group discussions and other proposed methods in Gdynia, Warsaw, Lublin, Wroclaw, Rzeszow, Przemysl and Krakow.

Develop a minimum of 4 case studies which showcase good practice in terms of accessibility and inclusivity of public participation mechanisms towards displacement affected persons in Poland

Develop recommendations specific to mentioned geographical areas on short- and medium-term measures to improve accessibility of public participation mechanisms towards displacement affected persons.

Deliver operationalization workshops and awareness raising materials informed by the research recommendations for representatives of Polish and Ukrainian civil society, public servants and youth, with consideration to age, gender and diversity.

Key responsibilities:

Scope of research

The study comprises the investigative part and the practical part. The following tasks and areas of implementation are envisaged for the successful implementation.

Geographical area of focus:

The voivodships of implementation of the Community Centers/Blue Dots project: Dolnośląskie, Lubelskie, Małopolskie, Mazowieckie, Podkarpackie, Pomorskie specifically Gdynia, Warsaw, Lublin, Wroclaw, Rzeszow, Przemysl, Krakow. Ideally the research would cover all locations. At minimum the research should cover 3 locations in different voivodships.

Key tasks:

- Mapping of participatory mechanisms existing at municipal level with the detailed description of the scope of their functionality, relevance and accessibility towards displacement-affected persons from Ukraine and other countries with consideration of different age groups.

- Mapping of participatory budgets and other micro-grant mechanisms for community-driven initiatives and their relevance and accessibility towards displacement-affected persons from Ukraine and other countries.

- Develop research methodology to identify barriers and opportunities to access public participation mechanisms by displacement-affected persons of different age in collaboration with DRC and project partners. The methodology should include desk research analysis of existing documents, processes and policies; as well as qualitative  methods of data collection (at minimum key informant interviews with public institution staff and refugee activists/community-based organization, FGDs with refugee activists, members community-based organization).

- Conduct research on barriers and opportunities to access public participation mechanisms by displacement-affected persons of different age.

- Develop at least 4 case studies showcasing relevant practice on enhancing accessibility of public participation mechanisms towards refugees, migrants and asylum seekers of different age and gender groups.

- Develop a narrative report, which will contain the analysis of findings per area and aggregated, and area specific recommendations for different stakeholders (civil society, NGOs, public institutions).

- Based on the results of the conducted research and mapping, prepare the dissemination materials on procedures and regulations regarding involvement and participation in the civic engagement mechanisms, adjusted to the local context.

- Delivering 2 workshops where the results of the mapping and research will be presented and operationalised for the further application, that would constitute the practical part of the study. One set of workshops should target representatives of Ukrainian and Polish civil society, as well as public servants (e.g. teachers, civil servants etc). The second set of workshop should target representatives of youth from host community and displacement-affected communities.

Key deliverables/outputs

- Inception report including desk research and developed methodology for barrier and opportunity mapping on increasing accessibility of public participation mechanisms

- Final report for validation including mapping (of participatory mechanism, budgets, etc), research findings, case studies and recommendation in Polish, English (possibly also in Ukrainian and Russian).

- Scripts of the workshops on presenting the results of research, specifying the modules and timelines,

- Dissemination materials on ways in which displaced persons can access existing public participation mechanisms adjusted to the local context.

- Dissemination and operationalization workshops covering all geographical areas for civil society, public servants and youth, as described above.

Functional competencies (Company Profile):

The eligible services provider should have staff with the following qualifications and experience:

- Minimum 5 years of experience in research of civic participation mechanisms and public policies in Poland and training for civil society organisations.

- Academic background in social sciences, social policy, migration studies, political science.

- Demonstrated professional experience and expertise in conducting similar studies in the areas of implementation and knowledge of the local context.

- Previous experience in conducting research in the public participation, human rights, social inclusion, and/or migration context with the application of culture- and conflict-sensitive approaches.

- Previous demonstrated experience on policy dialogue with municipalities.

- Previous experience in conducting workshops with the application of Adult Learning theory.

- Previous experience of working with the humanitarian INGOs will be an advantage.

Payment modality:

Payments will be made in instalments based on achieved milestones as agreed in the payment schedule following the issuance of invoices which will include VAT and confirmation of milestones achieved.

Proposal Evaluation:

For the award of this project, DRC has established evaluation criteria which govern the selection of offers received. The evaluation is made on a technical and financial basis. The percentage assigned to each component is determined in advance as follows:

The following selection criteria will be used for technical evaluation of the proposals:

| Description of Item | Weighting % |
| --- | --- |
| - Consultancy proposal outlining: - Proposed detailed methodology including detailed methods of data collection and proposed sample sizes where applicable - Description of groups included in the research - Geographical areas covered (minimum 3 however proposals including more areas will be scored higher) - Languages of deliverables (minimum expectation – Polish and English, ideally also Ukrainian and Russian) - Dissemination and recommendation operationalization plan through workshops and other activities - Proposed mode of collaboration with DRC - Detailed workplan indicating project milestones and deliverables | 35% |
| 2. Technical capacity (experience in delivering similar consultancies, number of staff, qualification of dedicated staff evidenced by respective CVs, previous research published, etc.) | 20% |
| 3. Ability to complete the consultancy within 75 working days | 15% |
| T4. Price – assessed based on detailed budget per deliverable and proposed instalment schedule | 30% |

Duration:

It is expected that the consultancy will take 75 working days starting from September 25th, 2023.

Confidentiality:

All information presented, obtained and produced is to be treated as DRC’s property and is considered as confidential for all other purposes than what is outlined in the ToR.

I certify that I have read, understood and agreed with the above document. I further certify that the below mentioned company has not engaged in corrupt, fraudulent, collusive, or coercive practices in competing for, or in executing, any Contracts.

In ____________________ on _________________2023.

Company name ________________________

Signature _____________________________    Comp. stamp